## Start Here
Freelance Project Tracker
Track clients, projects and tasks in one place, with an automatic overview of what is overdue and what is due next.
Quick start
1. Delete the SAMPLE rows on Clients, Projects and Tasks (see below).
2. Add your clients on "Clients" - give each a unique Client ID (e.g. C-001).
3. Add projects on "Projects" - give each a unique Project ID (e.g. P-001) and pick the Client ID from the drop-down. The client name fills in automatically.
4. Add tasks on "Tasks" - pick the Project ID, status and priority from the drop-downs, and enter a due date. When a task is finished set its status to Done and enter the done date.
5. Check "Overview" for counts, overdue work and upcoming deadlines.
IMPORTANT - sample data
The 5 clients, 7 projects and 21 tasks supplied are fictional SAMPLE data (names end in "(sample)" or notes say SAMPLE). Delete them before use.
How to delete: select the sample rows inside each table, right-click and choose Delete > Table Rows. Do this on Tasks first, then Projects, then Clients.
Sheet guide
Clients - client ID, name, contact person, email and notes.
Projects - project ID and name, client ID (drop-down), client name (looked up automatically), start date, deadline, budget, status, priority, % complete (calculated from tasks marked Done) and days to deadline.
Tasks - task, project ID (drop-down), owner, status (Not started / In progress / Blocked / Done), priority (Low / Medium / High / Urgent), due date, done date and days overdue (calculated).
Overview - counts by status and priority, overdue tasks and projects, and deadlines inside the "upcoming window".
Report date and upcoming window
Overview cell B3 holds the report date. It is =TODAY() so the workbook always reports "as of today". To see the position on another date, type a date into B3; to go back, enter =TODAY() again.
Overview cell B4 sets the upcoming window in days (default 14). "Due soon" counts include items due from the report date up to report date + window.
Rules used by the calculations
- A task is overdue when its status is not Done and its due date is before the report date. Days overdue = report date minus due date.
- A project counts as open unless its status is Completed or Cancelled. Open projects past their deadline are flagged red; deadlines inside the window are amber.
- % complete = tasks marked Done / all tasks for that project (0% when a project has no tasks yet).
Tips
- To add a row, type in the first empty row directly under a table - the table grows automatically and the calculated columns are already filled in. Calculations read rows 5 to 1000.
- Keep IDs unique and type them exactly the same way on every sheet (the drop-downs help).
- Shaded cells contain formulas - do not type over them.
Compatibility
Built for Microsoft Excel 2016+ and compatible spreadsheet apps; formulas verified with an automated recalculation test.
The workbook uses only standard functions (COUNTIFS, SUMIFS, INDEX, MATCH, IFERROR, TODAY and similar) - no macros, no external links, no dynamic-array functions.

## Overview
Overview
Report date (=TODAY() by default; type a date to override) | 2026-10-28
Upcoming window (days) | 14
Tasks by status |  |  | Projects by status
Status | Tasks | Share | Status | Projects
Not started | 7 | 33.33% | Planned | 1
In progress | 4 | 19.05% | Active | 3
Blocked | 2 | 9.524% | On hold | 1
Done | 8 | 38.1% | Completed | 1
|  |  | Cancelled | 1
Tasks by priority |  |  | Projects by priority
Priority | All tasks | Open tasks | Priority | All | Open
Low | 4 | 1 | Low | 2 | 0
Medium | 7 | 4 | Medium | 2 | 2
High | 7 | 5 | High | 2 | 2
Urgent | 3 | 3 | Urgent | 1 | 1
Key metrics
Metric | Value
Total tasks | 21
Open tasks (not Done) | 13
Overdue tasks | 3
Open tasks due in the next 14 days | 5
Most overdue task (days) | 12
Tasks completed in the last 14 days | 0
Open projects (not Completed / Cancelled) | 5
Open projects past deadline | 0
Project deadlines in the next 14 days | 2
Budget of open projects | 14650
Average % complete of open projects | 23%

## Clients
Clients
SAMPLE DATA: rows 5-9 are fictional. Delete them (select rows > right-click > Delete > Table Rows) before use.
Client ID | Client name | Contact person | Email | Notes
C-001 | Maple & Finch Interiors (sample) | Jordan Ellery | jordan@maplefinch.example | SAMPLE - Prefers email; invoices monthly
C-002 | Copperleaf Cafe (sample) | Priya Hollis | priya@copperleaf.example | SAMPLE - Weekly check-in on Mondays
C-003 | Fernhill Physio (sample) | Marcus Dunmore | marcus@fernhill.example | SAMPLE - Needs accessible booking flow
C-004 | Northgate Community Library (sample) | Ada Penrose | ada@northgate.example | SAMPLE - Purchase order required
C-005 | Brightwater Dental (sample) | Leo Ashcombe | leo@brightwater.example | SAMPLE - Retainer client

## Projects
Projects
SAMPLE DATA: rows 5-11 are fictional. Delete them before use. Shaded columns are calculated.
Project ID | Project name | Client ID | Client name | Start date | Deadline | Budget | Status | Priority | % complete | Days to deadline
P-001 | Website refresh (sample) | C-001 | Maple & Finch Interiors (sample) | 2026-09-01 | 2026-11-10 | 4200 | Active | High | 40% | 13
P-002 | Brand guidelines (sample) | C-002 | Copperleaf Cafe (sample) | 2026-09-15 | 2026-10-30 | 1800 | Active | Urgent | 50% | 2
P-003 | Booking app prototype (sample) | C-003 | Fernhill Physio (sample) | 2026-10-05 | 2026-12-15 | 6500 | Active | Medium | 25% | 48
P-004 | SEO audit (sample) | C-001 | Maple & Finch Interiors (sample) | 2026-08-01 | 2026-09-15 | 900 | Completed | Low | 66.67% | -43
P-005 | Newsletter templates (sample) | C-004 | Northgate Community Library (sample) | 2026-10-20 | 2026-11-14 | 750 | Planned | Medium | 0% | 17
P-006 | Photo edits (sample) | C-005 | Brightwater Dental (sample) | 2026-07-10 | 2026-08-30 | 1200 | Cancelled | Low | 100% | -59
P-007 | Social media kit (sample) | C-002 | Copperleaf Cafe (sample) | 2026-11-01 | 2026-12-05 | 1400 | On hold | High | 0% | 38

## Tasks
Tasks
SAMPLE DATA: rows 5-25 are fictional. Delete them before use. "Days overdue" is calculated against the report date on Overview.
Task | Project ID | Owner | Status | Priority | Due date | Done date | Days overdue
Content audit (sample) | P-001 | Me | Done | Medium | 2026-09-12 | 2026-09-11 | 0
Wireframes (sample) | P-001 | Me | Done | High | 2026-09-26 | 2026-09-29 | 0
Homepage design (sample) | P-001 | Sam (contractor) | In progress | High | 2026-10-20 |  | 8
Build page templates (sample) | P-001 | Me | In progress | High | 2026-11-05 |  | 0
Launch checklist (sample) | P-001 | Me | Not started | Medium | 2026-11-09 |  | 0
Moodboard (sample) | P-002 | Me | Done | Medium | 2026-09-25 | 2026-09-24 | 0
Logo refinements (sample) | P-002 | Alex (contractor) | Done | High | 2026-10-10 | 2026-10-12 | 0
Colour & type spec (sample) | P-002 | Me | Blocked | Urgent | 2026-10-24 |  | 4
Guidelines PDF (sample) | P-002 | Me | Not started | Urgent | 2026-10-29 |  | 0
Discovery call notes (sample) | P-003 | Me | Done | Low | 2026-10-07 | 2026-10-07 | 0
User flows (sample) | P-003 | Me | In progress | High | 2026-10-28 |  | 0
Clickable prototype (sample) | P-003 | Sam (contractor) | Not started | High | 2026-11-20 |  | 0
Usability test (sample) | P-003 | Me | Not started | Medium | 2026-12-04 |  | 0
Crawl report (sample) | P-004 | Me | Done | Low | 2026-08-15 | 2026-08-14 | 0
Recommendations document (sample) | P-004 | Me | Done | Medium | 2026-09-10 | 2026-09-12 | 0
Template wireframes (sample) | P-005 | Me | Not started | Medium | 2026-11-04 |  | 0
Test sends (sample) | P-005 | Me | Not started | Low | 2026-11-12 |  | 0
Select images (sample) | P-006 | Me | Done | Low | 2026-07-20 | 2026-07-20 | 0
Content calendar (sample) | P-007 | Alex (contractor) | Blocked | Medium | 2026-11-25 |  | 0
Template set (sample) | P-007 | Me | Not started | High | 2026-12-02 |  | 0
Invoice final payment (sample) | P-004 | Me | In progress | Urgent | 2026-10-16 |  | 12